## Instructions
HOW TO USE THIS WORKPLAN
1. In the Exposure sheet, count exposed people by site and role.
2. List the main hazards in sections A (Safety) and B (Health).
3. Adapt the management processes in section C to your company.
4. Use the Risk Matrix sheet to assess risk from exposure and severity.
5. Define control measures or safety objectives using the STOP principle.
6. Enter specific actions in the quarterly columns.
COLOURS FOR QUARTERLY CELLS
White background with text = planned
Green background = complete
Yellow background = in progress (optional)
Legal basis: VUV Arts. 3–10, UVG Art. 82, FCOS Directive 6508

## Workplan
SAFETY ROADMAP: WORKPLAN
Grey italic text = examples. Replace with your company’s priorities. Colour quarterly cells green when actions are complete.
Vision / target | Zero accidents and occupational diseases. Annual target (example): 30% reduction in [metric] vs [baseline year].
[6 empty] | 2026 |  |  |  | 2027 |  |  |  | 2028
Topic | Exposed people | Exposure frequency | Severity / Consequences | Risk | Controls / Safety objective | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
A: SAFETY
Falls and trips |  | High | Sprains and fractures | Medium | Housekeeping, safe walkways
Hand tools |  | Medium | Cuts and eye injuries | Medium | PPE, safety signs, safe-use instruction
Machines and equipment |  | Low | Amputations, death | High | Machine guards, machine safety rules
Vehicles and traffic routes |  | Medium | Fractures, death | High | Traffic management plan, forklift safety rules
Confined spaces |  | Low | Death | High | Training, rescue drills
Work at height |  | Low | Fractures, death | High | Equipment checks, collective fall protection, personal protection where required
Electrical safety |  | Low | Burns, electric shock | High | Electrical safety plan, audits
B: HEALTH
Noise |  | Medium | Hearing loss | Medium | Noise map, hearing protection zones
Dust / welding fumes |  | Medium | Silicosis, cancer | High | Local exhaust ventilation, exposure monitoring against Swiss limits
Chemicals |  | Low | Harm to health | Low | Chemical inventory, safe storage conditions
Ergonomics |  | High | Musculoskeletal disorders | Medium | Workplace assessments, lifting aids
Skin protection |  | Medium | Dermatitis | Low | Skin protection products, skin-care instruction
Stress |  | Medium | Mental ill health | Medium | S-Tool survey, action plan
C: SUPPORT PROCESSES
Incident handling |  |  |  |  | Investigate all accidents and near misses
Safety conversations |  |  |  |  | Line managers inspect workplaces and hold safety conversations
Hazard identification |  |  |  |  | Job safety analysis for high-risk work, workplace risk assessment
Training and communication |  |  |  |  | Competence matrix, toolbox talks, induction
Permit to work |  |  |  |  | Permits for hot work, work at height, confined spaces and energy isolation
Contractor management |  |  |  |  | Contractor induction, supervision and evaluation
KPIs | Results: accident count, lost days per accident. Prevention: safety conversations per manager, reports of near misses and unsafe situations, audit findings.

## Exposure
EXPOSURE: EXPOSED PEOPLE BY SITE AND ROLE
Count exposed people by site/unit and role. Adapt the example categories to your company.
Add rows and columns as needed and extend the total formulas.
Site / Unit | Production A | Production B | Machine operators | Drivers | Logistics | Maintenance | Workshop | Cleaning | Laboratory | Administration | Total
Site 1 | [10 empty] | 0
Site 2 | [10 empty] | 0
Site 3 | [10 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Risk Matrix
RISK MATRIX
Severity
|  | Medical treatment | Lost time > 1 day | Disability or death
Exposure | High | Medium | High | High
| Medium | Low | Medium | High
| Low | Low | Medium | High
Quarterly cell colours
| White + text | Planned
| Green background | Complete
| Yellow background | In progress (optional)